## Sheet1
main |  | sub | task | startdate | finishdate
1 |  |  | Create a database using SQLite
1 |  | 1 | Create SQL script to build up a db | 20200619 | 20200621
1 |  | 2 | Create python script to insert data into db | 20200619 | 20200621
2 |  |  | insert metafile for mapping in db
2 |  | 1 | geography | 20200621 | 20200621
2 |  | 2 | industry | 20200621 | 20200622
2 |  | 3 | product_code(sitc, hs items) | 20200621 | 20200622
2 |  | 4 | sitc2hs | 20200621 | 20200621
3 |  |  | acquire data from db
3 | a | 1 | acquire hsccit, hscoit, hscoccit data respectively with periods assigned | 20200623
|  | 2 | merge them | 20200623
3 | b |  | for country
|  | 1 | general_trade figures, ranking (multiple periods) | 20200623 | 20200623
|  | 2 | TX, DX, RX, IM by product ranking (one period) | 20200623
4 |  |  | automate R1 reports
5 |  |  | GUI tkinter